Relicensing Schedule Using the Traditional Licensing Process for the Lake Lynn Project (Updated November 6, 2019)

|  |  |  |  |
| --- | --- | --- | --- |
| **Activity** | **Responsibility** | **Timeframe and Regulations** | **Dates1** |
| File NOI, PAD, and Request to use TLP and publish Public Notice in newspaper | Lake Lynn | 5 to 5½ years prior to license expiration | August 29, 2019 |
| File verification of Public Notice with FERC | Lake Lynn | Within two weeks of filing the NOI, PAD, and Request to use the TLP | September 11, 2019 |
| Comments on TLP Request | FERC, Relicensing Participants | Within 30 days of NOI/PAD/TLP request filing and newspaper notice | September 28, 2019 |
| FERC issues Notice of Commencement | FERC | Within 60 days of PAD/NOI/TLP request filing | October 17, 2019 |
| FERC approves use of TLP | FERC | Within 60 days of PAD/NOI/TLP request filing | October 17, 2019 |
| Notify FERC of Joint Meeting and publish Notice in newspaper | Lake Lynn | At least 15 days in advance of meeting | November 22, 2019 |
| Joint Meeting for consultation with agencies, tribes and interested public | Lake Lynn | 30-60 days following FERC approval of TLP | December 12, 2019 |
| Comments and Study Requests | Relicensing Participants | Due 60 days after Joint Meeting | February 10, 2020 |
| Study Plan Development | Lake Lynn | Ongoing following Joint Meeting | December 12-March 1, 2020 |
| Conduct Field Studies | Lake Lynn | One season of field studies | April 1-November 1 2020 |
| DLA and Study Results | Lake Lynn | Produced following conclusion of studies | November 30, 2021 |
| Comments on DLA | Relicensing Participants | 90-day comment period | February 28, 2022 |
| FLA filed with FERC | Lake Lynn | 2 years prior to license expiration | November 30, 2022 |
| FERC issues Public Notice of Application | FERC | Within 14 days of FLA submittal | December 14, 2022 |
| FERC Issues New License on or before License Expiration Date | FERC |  | November 30, 2024 |

1 If the due date falls on a weekend or a holiday, the due date is the subsequent business day.